## Sheet1
National Disaster Resiliency Competition and Long-Term Commitment Schedule
2014-09-17 | HUD posted the NDRC Notice of Funding Availability (NDRC NOFA)
2015-01-15 | Stakeholder Meeting - Tuolumne County
2015-02-03 | California NDRC Website goes live: http://www.hcd.ca.gov/NationalDisaster/ResilienceCompetition.html
2015-02-18 | Public comment opens on required parts of the Phase 1 Application
2015-03-02 | Public hearing in Tuolumne County on the Application parts posted for public comment
2015-03-03 | Public Information Webinar on the Application parts posted for public comment
March, 10, 2015 (5:00pm) | Public comment closes on required parts of the Phase 1 Application
2015-03-27 | Phase 1 Application Due to HUD via Grants.gov
March-June 2015 | HUD Phase 1 Application reviews and invitations extended for Phase 2 Applications
April - October 2015 | Monthly Stakeholder Meetings - Tuolumne County
May - October 2015 | Core Team* and Stakeholders develop and draft Phase 2 projects and secure leveraged funding sources and prepare final Phase 2 Application pieces
December, 2015 | Announcement of Phase 2 winners / Funding levels announced for all successful applicants
Early 2016 | Grant agreements signed and sent to successful applicants
* Core Team | Governor's Office of Planning and Research (OPR), California Department of Housing and Community Development (HCD), Tuolumne County, California Environmental Protection Agency (CalEPA), California Department of Forestry and Fire Protection (CalFire), US Forest Service, and the California Conservation Corps. (CCC)
Initial Long-Term Commitment Framework
2015-02-20 | Forest Climate Action Team (FCAT) Forest Carbon Plan Public Hearings
2015-03-02
2015-03-11
March - April | Compliation of final FCAT Forest Carbon Plan
2016-05-01 | Climate Action Team Forest Carbon Plan completed
2015-04-01 | Green House Gas Reduction Fund Public and Stakeholder Outreach by CalEPA
Ongoing | Fire break work by CalFire
Ongoing | US Forest Service reforestation work / Biomass removal