Residential Relocation Project Planning Checklist             											Appendix VII-C

This Planning Checklist is intended as a tool for grantees managing HCD/HUD projects that require residential displacement. The checklist will not be applicable to all relocation projects. It does not address business relocation. HCD/HUD may require additional or alternative tasks related to your specific project. Please seek the advice of your HCD/HUD contact prior to project initiation.

Assumption:  Property acquired through negotiation without the threat of eminent domain.

| Scheduled | Task | Form Reference* | √ |
| --- | --- | --- | --- |
|  | Identify Property and Initiate Discussions with Property Owner |  |  |
|  | Submit Application for Funding to HCD/HUD |  |  |
|  | Secure Tenant List and Copies of Rental/Lease Agreements |  |  |
|  | Prepare and deliver General Information Notices. Document delivery. Provide copies of Notices to HCD. | 1378, App. 2, 3, or 4 |  |
|  | Prepare an Initial Contact Letter Introducing the Project, Schedule, and Staff and Requesting an Interview with Tenant |  |  |
|  | Conduct an Initial Interview with each household. Deliver appropriate Relocation Handbook. Complete “Site Occupant Record”, “Certification of Occupancy”, and “Income Certification” forms. | HUD 1041, 1042 and 1043 1378, App. 8 or 9 |  |
|  | Prepare “Notice to Prospective Tenants” (“Move In Notice”) and have the Property Manager present it to each household prior to occupancy. Notice must be signed by prospective tenants to certify delivery. | 1378, App. 29 |  |
|  | Prepare a Relocation Impact Study and Last Resort Housing Plan | Model Relocation Plan HCD-832 www.hcd.ca.gov |  |
|  | Circulate Plan for a 30-Day Review and Comment Period. A notice of Plan availability needs to be delivered to each household. Send Plan to HCD and HUD for review and comment. Also send to “all interested parties”. |  |  |
|  | Finalize Plan by incorporating and responding to all comments received from the public. |  |  |
|  | Arrange to have Plan placed on Agency Board or Governing Board Agenda. |  |  |
|  | When notified that funding is approved, provide household with either a “Notice of Eligibility” or “Notice of Non-Displacement” as needed. Certify delivery. Copies to HCD. | 1378, App. 4, 5, 6, 7, 25 or 26 |  |
|  | Determine the cost of Comparable Replacement Housing. Conduct a Housing Study. Copies to HCD. | HUD Form 40061 |  |
|  | Prepare and deliver “Notices of Entitlement” for Permanently Displaced Households. Certify delivery. Copies to HCD. | HUD Form 40057, 40058 or 40072 |  |
|  | Prepare and deliver “Notice of Temporary Relocation Assistance” for Temporarily Displaced Households that describes the project scope, schedule, and the particular impact on the household. Certify delivery. Copies to HCD. |  |  |
|  | Provide Relocation Advisory Services to all households. Help to locate and secure replacement housing, file claims, etc. |  |  |
|  | Deliver 90-Day Notices to Vacate and 30-Day Notices to Vacate as needed. |  |  |
|  | Conduct Home Inspections as Replacement Sites are Identified. Homes must be Decent, Safe and Sanitary (“DS&S”). | 1378, App. 11 |  |
|  | Develop a Payment Schedule and disburse payments accordingly. Document all payments. |  |  |
|  | Organize Files and copy HCD. Include completed HUD Form 40054 and documentation of payment. |  |  |

*HUD Handbook 1378, Change 4 or HUD Forms (www.hudclips.org)