Residential Relocation Program Planning Checklist

This Planning Checklist is intended as a tool for grantees managing HCD/HUD projects that require residential displacement. The checklist will not be applicable to all relocation projects. It does not address business relocation. HCD/HUD may require additional or alternative tasks related to your specific project. Please seek the advice of your HCD/HUD contact prior to project initiation.

Assumption:  Property acquired through negotiation without the threat of eminent domain.

| Scheduled | Task | Form Reference* | √ |
| --- | --- | --- | --- |
|  | Identify Property and Initiate Discussions with Property Owner |  |  |
|  | If offer is accepted submit required paperwork to State recipient. |  |  |
|  | Secure Tenant’s names copy of Rental/Lease Agreement |  |  |
|  | Prepare and deliver General Information Notices. Document delivery. Provide copies of Notices to HCD. | 1378, App. 2, 3, or 4 |  |
|  | Prepare an Initial Contact Letter Introducing the Program, Schedule, and Staff and Requesting an Interview with Tenant |  |  |
|  | Conduct an Initial Interview with the household. Deliver appropriate Relocation Handbook. Complete “Site Occupant Record”, “Certification of Occupancy”, and “Income Certification” forms. | HUD 1041, 1042 and 1043 1378, App. 8 or 9 |  |
|  | Prepare “Notice to Prospective Tenants” (“Move In Notice”) and have the owner present it to any new household that moves in prior to loan closing. Notice must be signed by prospective tenants to certify delivery. | 1378, App. 29 |  |
|  | Ensure that the relocation cover letter specifies the subject address and references to the State Recipient’s approved Relocation Plan. | Model Relocation Plan HCD-832 www.hcd.ca.gov |  |
|  | When notified that funding is approved, provide the household with either a “Notice of Eligibility” Notice of Non-Displacement if funding is not approved. Certify delivery with copies to HCD. | 1378, App. 4,5,6,7, 25, or 26 |  |
|  | Determine the cost of Comparable Replacement Housing. Conduct a housing study with copies to HCD. | HUD Form 40061 |  |
|  | Provide Relocation Advisory Services to all households. Help to locate and secure replacement housing, file claims, etc. |  |  |
|  | Deliver 90 Day Notice to Vacate and 30 Day Notice to Vacate as needed. |  |  |
|  | Conduct Home Inspections for replacement housing for decent, safe & sanitary standards. | 1378, App. 11 |  |
|  | Develop a payment schedule and disburse payments accordingly. |  |  |
|  | Organize files and include a copy of the completed HUD Form 40054 and documentation of payments to HCD |  |  |

*HUD Handbook 1378, Change 4 or HUD Forms (www.hudclips.org)