## 2023 24 $
State of California
Grant: B-25-DU-06-0001
Program Expenditure Projections
*This budget total reflects actuals through the last day of the previous quarter.
**This budget total reflects program budgets as of the original Action Plan
[6 empty] | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Original AP Budget | Current APA Budget** | Actuals* | Budget Remaining | Total Projected | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
B-25-DU-06-0001 Homebuyer Assistance Program (HBA) | [5 empty] | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Original AP Budget | Current APA Budget** | Actuals* | Budget Remaining | Total Projected | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
HBA | 14686880 | 14686880 | 0 | 14686880 | 14686880 | 9400 | 35000 | 60000 | 5430446.5 | 7840446.5 | 75000 | 80000 | 100000 | 100000 | 150000 | 150000 | 100000 | 100000 | 75000 | 75000 | 50000 | 50000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 26587
B-25-DU-06-0001 Single-Family Rehab/Reconstruction Program (SFRR)​​ | [5 empty] | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Original AP Budget | Current APA Budget** | Actuals* | Budget Remaining | Total Projected | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
SFRR | 52814040 | 52814040 | 0 | 52814040 | 52814040 | 56700 | 290000 | 497375.56 | 1122216.17 | 1531083.67 | 3301984.27 | 3323657.94 | 14713657.94 | 19718657.94 | 5548657.94 | 497375.57 | 300000 | 250000 | 250000 | 200000 | 200000 | 200000 | 150000 | 150000 | 150000 | 150000 | 100000 | 100000 | 12673
B-25-DU-06-0001 Multifamily Housing Program (MHP) | [5 empty] | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Original AP Budget | Current APA Budget** | Actuals* | Budget Remaining | Total Projected | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
MHP | 155695585 | 155695585 | 0 | 155695585 | 155695585 | 7000 | 86800 | 90000 | 120000 | 150000 | 7165328.81 | 7265328.8 | 14280657.61 | 21295986.41 | 28261315.22 | 28311315.22 | 14430657.61 | 7715328.81 | 7965328.81 | 7965328.7 | 1000000 | 1200000 | 1500000 | 1700000 | 1600000 | 1700000 | 1000000 | 485000 | 400209
B-25-DU-06-0001 Tribal (Hoopa Valley Tribe Set-Aside​​ & Tule River Tribe Set-Aside​​) | [5 empty] | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Original AP Budget | Current APA Budget** | Actuals* | Budget Remaining | Total Projected | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Tribal | 22576000 | 22576000 | 0 | 22576000 | 22576000 | 12200 | 44000 | 44000 | 44000 | 84000 | 110000 | 60000 | 60000 | 140000 | 125000 | 1100000 | 2100000 | 2150000 | 2150000 | 2150000 | 400000 | 5150000 | 1150000 | 2150500 | 2150000 | 839079 | 160000 | 125000 | 78221
B-25-DU-06-0001 Infrastructure Program | [5 empty] | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Original AP Budget | Current APA Budget** | Actuals* | Budget Remaining | Total Projected | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
INFRA | 95655645 | 95655645 | 0 | 95655645 | 95655645 | 53800 | 153000 | 225000 | 1100000 | 1650000 | 1900000 | 2200000 | 3200000 | 4250000 | 5300000 | 5300000 | 5300000 | 5450000 | 5450000 | 7500000 | 8300000 | 8300000 | 8300000 | 8250000 | 4301630 | 4250000 | 3250000 | 1172215 | 500000
B-25-DU-06-0001 Mitigation Set-Aside | [5 empty] | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Original AP Budget | Current APA Budget** | Actuals* | Budget Remaining | Total Projected | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
MIT Set-Aside | 54339000 | 54339000 | 0 | 54339000 | 54339000 | 24800 | 75000 | 183000 | 703000 | 1020000 | 1135000 | 1315000 | 1865000 | 2180000 | 2318978.32 | 2323978.32 | 2873978.32 | 3091934.97 | 3398869.94 | 4784783.24 | 4839783.24 | 4899783.24 | 4749783.24 | 4689783.24 | 3214891.62 | 2593373.31 | 1235000 | 685000 | 138279
Mitigation-Resilient Infrastructure and Planning Program (MIT-RIPP) | 46839000 | 46839000 | 0 | 46839000 | 46839000 | 24800 | 75000 | 120000 | 500000 | 810000 | 925000 | 1100000 | 1650000 | 2150000 | 2200000 | 2200000 | 2750000 | 2800000 | 2850000 | 3900000 | 3950000 | 4000000 | 3850000 | 3800000 | 2750000 | 2474395 | 1200000 | 650000 | 109805
Insurance Resilience Planning Program (IRPP) | 7500000 | 7500000 | 0 | 7500000 | 7500000 | 0 | 0 | 63000 | 203000 | 210000 | 210000 | 215000 | 215000 | 30000 | 118978.32 | 123978.32 | 123978.32 | 291934.97 | 548869.94 | 884783.24 | 889783.24 | 899783.24 | 899783.24 | 889783.24 | 464891.62 | 118978.31 | 35000 | 35000 | 28474
B-25-DU-06-0001 Administration | [5 empty] | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Original AP Budget | Current APA Budget** | Actuals* | Budget Remaining | Total Projected | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Admin | 20829850 | 20829850 | 0 | 20829850 | 20829850 | 0 | 0 | 0 | 100000 | 100000 | 100000 | 100000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1500000 | 1500000 | 2000000 | 1500000 | 1500000 | 1429850
Updated Q1 2026

## 2023 24 #
State of California
Grant: B-25-DU-06-0001
Program Performance Outcomes Projections
*Difference is calculated as Projections - Actuals
[6 empty] | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Outcome | Program Goal | Actuals | Total Projected | Difference* | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Projected
B-25-DU-06-0001 Homebuyer Assistance Program (HBA) | [5 empty] | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Outcome | Program Goal | Actuals | Total Projected | Difference* | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Projected
HBA | # of housing units | 40 | 0 | 40 |  | 0 | 0 | 0 | 16 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40
B-25-DU-06-0001 Single-Family Rehab/Reconstruction Program (SFRR)​​ | [5 empty] | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Outcome | Program Goal | Actuals | Total Projected | Difference* | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Projected
SFRR | # of housing units | 96 | 0 | 96 |  | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 31 | 45 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96
B-25-DU-06-0001 Multifamily Housing Program (MHP) | [5 empty] | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Outcome | Program Goal | Actuals | Total Projected | Difference* | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Projected
MHP | # of multifamily units | 261 | 0 | 261 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261
B-25-DU-06-0001 Tribal (Hoopa Valley Tribe Set-Aside​​ & Tule River Tribe Set-Aside​​) | [5 empty] | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Outcome | Program Goal | Actuals | Total Projected | Difference* | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Projected
Tribal | # planning studies | 2 | 0 | 2 |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
B-25-DU-06-0001 Infrastructure Program | [5 empty] | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Outcome | Program Goal | Actuals | Total Projected | Difference* | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Projected
Infrastructure | # infrastructure improvement project | 42 | 0 | 42 |  | 0 | 0 | 1 | 0 | 1 | 3 | 2 | 3 | 13 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 5 | 9 | 1 | 2 | 0 | 0 | 0 | 0 | 42
B-25-DU-06-0001 Mitigation Set-Aside | [5 empty] | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Outcome | Program Goal | Actuals | Total Projected | Difference* | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Projected
Mitigation-Resilient Infrastructure and Planning Program (MIT-RIPP) | # infrastructure improvement project | 21 | 0 | 21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 4 | 1 | 4` | 5 | 3 | 0 | 1 | 0 | 0 | 21
Mitigation-Resilient Infrastructure and Planning Program (MIT-RIPP) | # of planning studies | 7 | 0 | 7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
Insurance Resilience Planning Program (IRPP) | # planning studies | 1 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
B-25-DU-06-0001 Administration | [5 empty] | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Outcome | Program Goal | Actuals | Total Projected | Difference* | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Projected
Admin |  | 0 | 0 | 0 | [25 empty] | 0
Updated Q1 2026

## 2018-calculations (hidden)
| Original | APA1 | APA2 | APA3 | APA4 | APA5 | APA6 | APA7 | APA8 | APA9 | Running Total | Grant Breakdown File - May | Q1 2025 QPR
Housing |  | APA2: 48%; APA3: 52% |  |  | B-19-DV-06-0001 | B-19-DV-06-002 | QPR TOTAL
OOR | 205107638 | APA2: 2000000; APA4: 15275984.19; APA7: -105220977.02; APA9: -22554540 | 94608105.17 | 117162645.15 | 87087786.41 | 30226625.81 | 117314412.22 | FALSE
Multifamily | 250687114 | APA4: 30452393.36; APA7: 87550273; APA9: 22554540 | 391244320.36 | 368689780.36 | 147652133.88 | 221037646.48 | 368689780.36 | FALSE
Homebuyer Assistance |  | APA2: 26000000; APA4: 332686.65; APA7: 16344239.27; APA9: 0 | 42676925.92 | 42676925.93 | 20893219.48 | 21783706.43 | 42676925.91 | FALSE
Infrastructure | [10 empty] | 0 | 0 |  |  | 0 | TRUE
Local/FEMA Match | 317428488 | APA4: 41920212.8; APA7: 319486 | 359668186.8 | 359668186.81 | 188342800.61 | 171252537.99 | 359595338.6 | FALSE
Paradise Sewer |  | APA2: 30000000; APA4: 0; APA7: 0 | 30000000 | 30000000 | 0 | 30000000 | 30000000 | TRUE
Economic Revitalization | [10 empty] | 0 | 0 |  |  | 0 | TRUE
Workforce Development | 40695960 | APA4: 5846412.33; APA7: 1006978.75 | 47549351.08 | 47549351.09 | 22871159.06 | 24287583.41 | 47158742.47 | FALSE
Planning | [10 empty] | 0 | 0 |  |  | 0 | TRUE
Technical Assistance | 15000000 | APA4: -15000000 | 0 | 0 | 160420.27 | 36961.38 | 197381.65 | FALSE
Regional & Local | 71217000 | APA2: -58000000; APA4: -12434839.33 | 782160.67 | 782160.67 | 217680.29 | 367098.73 | 584779.02 | FALSE
State & Local | 66392850 | APA1: -66392850; APA4: 0 | 0 | 0 | 0 | 0 | 0 | TRUE
State and Local Program Delivery | 0 | APA1: 66392850; APA4: -66392850 | 0 | 0 |  |  | 0 | TRUE
Administration | 50869950 | [9 empty] | 50869950 | 50869950 | 24590800 | 26279150 | 50869950 | TRUE
| 1017399000 | [9 empty] | 1017399000 | 1017399000.01 |  |  | 1017087310.23 | FALSE
[15 empty] | 311689.77 | FALSE
|  | 31868568 | 960000
|  | 34524282 | 1040000
12480000
13520000
Housing
[8 empty] | OOR | #REF! | #REF!
[8 empty] | Multifamily | #REF! | #REF!
[8 empty] | Homebuyer Assistance | #REF! | #REF!
[8 empty] | Infrastructure |  | TRUE
[8 empty] | Local/FEMA Match | #REF! | #REF!
[8 empty] | Paradise Sewer | #REF! | #REF!
[8 empty] | Economic Revitalization |  | TRUE
[8 empty] | Workforce Development | #REF! | #REF!
[8 empty] | Planning |  | TRUE
[8 empty] | Technical Assistance | #REF! | #REF!
[8 empty] | Regional & Local | #REF! | #REF!
[8 empty] | State & Local |  | TRUE
[8 empty] | State and Local Program Delivery |  | TRUE
[8 empty] | Administration | #REF! | #REF!