## 2023 24 $
State of California
Grant: B-25-DU-06-0001
Program Expenditure Projections
*This budget total reflects actuals through the last day of the previous month.
**This budget total reflects program budgets as of the original Action Plan
[6 empty] | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Original AP Budget | Current APA Budget** | Actuals* | Budget Remaining | Total Projected | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
B-25-DU-06-0001 Homebuyer Assistance Program (HBA) | [5 empty] | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Original AP Budget | Current APA Budget** | Actuals* | Budget Remaining | Total Projected | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
HBA | 14686880 | 14686880 | 0 | 14686880 | 14686880 | 9400 | 35000 | 60000 | 5430446.5 | 7840446.5 | 75000 | 80000 | 100000 | 100000 | 150000 | 150000 | 100000 | 100000 | 75000 | 75000 | 50000 | 50000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 26587
B-25-DU-06-0001 Single-Family Rehab/Reconstruction Program (SFRR)​​ | [5 empty] | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Original AP Budget | Current APA Budget** | Actuals* | Budget Remaining | Total Projected | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
SFRR | 52814040 | 52814040 | 0 | 52814040 | 52814040 | 56700 | 290000 | 497375.56 | 1122216.17 | 1531083.67 | 3301984.27 | 3323657.94 | 14713657.94 | 19718657.94 | 5548657.94 | 497375.57 | 300000 | 250000 | 250000 | 200000 | 200000 | 200000 | 150000 | 150000 | 150000 | 150000 | 100000 | 100000 | 12673
B-25-DU-06-0001 Multifamily Housing Program (MHP) | [5 empty] | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Original AP Budget | Current APA Budget** | Actuals* | Budget Remaining | Total Projected | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
MHP | 155695585 | 155695585 | 0 | 155695585 | 155695585 | 7000 | 86800 | 90000 | 120000 | 150000 | 7165328.81 | 7265328.8 | 14280657.61 | 21295986.41 | 28261315.22 | 28311315.22 | 14430657.61 | 7715328.81 | 7965328.81 | 7965328.7 | 1000000 | 1200000 | 1500000 | 1700000 | 1600000 | 1700000 | 1000000 | 485000 | 400209
B-25-DU-06-0001 Tribal (Hoopa Valley Tribe Set-Aside​​ & Tule River Tribe Set-Aside​​) | [5 empty] | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Original AP Budget | Current APA Budget** | Actuals* | Budget Remaining | Total Projected | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Tribal | 22576000 | 22576000 | 0 | 22576000 | 22576000 | 12200 | 44000 | 44000 | 44000 | 84000 | 110000 | 60000 | 60000 | 140000 | 125000 | 1100000 | 2100000 | 2150000 | 2150000 | 2150000 | 400000 | 5150000 | 1150000 | 2150500 | 2150000 | 839079 | 160000 | 125000 | 78221
B-25-DU-06-0001 Infrastructure Program | [5 empty] | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Original AP Budget | Current APA Budget** | Actuals* | Budget Remaining | Total Projected | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
INFRA | 95655645 | 95655645 | 0 | 95655645 | 95655645 | 53800 | 153000 | 225000 | 1100000 | 1650000 | 1900000 | 2200000 | 3200000 | 4250000 | 4300000 | 4300000 | 5300000 | 5450000 | 5450000 | 5500000 | 8300000 | 8300000 | 8300000 | 8750000 | 4301630 | 4250000 | 3250000 | 2672215 | 2500000
B-25-DU-06-0001 Mitigation Set-Aside | [5 empty] | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Original AP Budget | Current APA Budget** | Actuals* | Budget Remaining | Total Projected | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
MIT Set-Aside | 54339000 | 54339000 | 0 | 54339000 | 54339000 | 24800 | 75000 | 183000 | 703000 | 1020000 | 1135000 | 1315000 | 1865000 | 2180000 | 2318978.32 | 2323978.32 | 2873978.32 | 3091934.97 | 3398869.94 | 3784783.24 | 4839783.24 | 4899783.24 | 4749783.24 | 4689783.24 | 3214891.62 | 2593373.31 | 1235000 | 1185000 | 638279
Mitigation-Resilient Infrastructure and Planning Program (MIT-RIPP) | 46839000 | 46839000 | 0 | 46839000 | 46839000 | 24800 | 75000 | 120000 | 500000 | 810000 | 925000 | 1100000 | 1650000 | 2150000 | 2200000 | 2200000 | 2750000 | 2800000 | 2850000 | 2900000 | 3950000 | 4000000 | 3850000 | 3800000 | 2750000 | 2474395 | 1200000 | 1150000 | 609805
Insurance Resilience Planning Program (IRPP) | 7500000 | 7500000 | 0 | 7500000 | 7500000 | 0 | 0 | 63000 | 203000 | 210000 | 210000 | 215000 | 215000 | 30000 | 118978.32 | 123978.32 | 123978.32 | 291934.97 | 548869.94 | 884783.24 | 889783.24 | 899783.24 | 899783.24 | 889783.24 | 464891.62 | 118978.31 | 35000 | 35000 | 28474
B-25-DU-06-0001 Administration | [5 empty] | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Original AP Budget | Current APA Budget** | Actuals* | Budget Remaining | Total Projected | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Admin | 20829850 | 20829850 | 0 | 20829850 | 20829850 | 0 | 0 | 0 | 100000 | 100000 | 100000 | 100000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1500000 | 1500000 | 2000000 | 1500000 | 1500000 | 1429850
Updated Q1 2026

## 2023 24 #
State of California
Grant: B-25-DU-06-0001
Program Performance Outcomes Projections
*Difference is calculated as Projections - Actuals
[5 empty] | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Outcome | Actuals | Total Projected | Difference* | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Projected
B-25-DU-06-0001 Homebuyer Assistance Program (HBA) |  |  |  |  | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Outcome | Actuals | Total Projected | Difference* | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Projected
HBA | # of housing units | 0 | 40 |  | 0 | 0 | 0 | 16 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40
B-25-DU-06-0001 Single-Family Rehab/Reconstruction Program (SFRR)​​ |  |  |  |  | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Outcome | Actuals | Total Projected | Difference* | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Projected
SFRR | # of housing units | 0 | 96 |  | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 31 | 45 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96
B-25-DU-06-0001 Multifamily Housing Program (MHP) |  |  |  |  | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Outcome | Actuals | Total Projected | Difference* | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Projected
MHP | # of multifamily units | 0 | 261 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261
B-25-DU-06-0001 Tribal (Hoopa Valley Tribe Set-Aside​​ & Tule River Tribe Set-Aside​​) |  |  |  |  | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Outcome | Actuals | Total Projected | Difference* | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Projected
Tribal | # planning studies | 0 | 2 |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
B-25-DU-06-0001 Infrastructure Program |  |  |  |  | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Outcome | Actuals | Total Projected | Difference* | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Projected
INFRA | # of linear feet of public improvements | 0 | TBD | [25 empty] | 0
| # of public facilities | 0 | TBD | [25 empty] | 0
B-25-DU-06-0001 Mitigation Set-Aside |  |  |  |  | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Outcome | Actuals | Total Projected | Difference* | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Projected
Mitigation-Resilient Infrastructure and Planning Program (MIT-RIPP) | # of linear feet of public improvements | 0 | TBD | [25 empty] | 0
| # of public facilities | 0 | TBD | [25 empty] | 0
| # of planning studies | 0 | TBD | [25 empty] | 0
Insurance Resilience Planning Program (IRPP) | # planning studies | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
B-25-DU-06-0001 Administration |  |  |  |  | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031
Program | Outcome | Actuals | Total Projected | Difference* | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Projected
Admin |  | 0 | 0 | [25 empty] | 0
Updated Q1 2026